## Slide 1: Robotics Projects
Ending first sprint and starting Sprint #2
Bookkeeping:
1) Make sure you have shared the team engineering notebook with
smithtitanrobotics@gmail.com!!!
2) Last page of notebook documents above and beyond for the first 6 weeks for each team member.
- Document if you will be helping at the ‘VEX Idea Factory’ on Saturday

## Slide 2: Learning Targets
Incorporate the Scrum framework in developing an awesome robot!
Today (and tomorrow if needed) we will focus on ..
  Sprint Review
  Spring Retrospective
  Revisiting and Improving on your team’s design direction
  Creating a Sprint Backlog
After the next sprint is our first tournament!!

## Slide 3: Sprint Review (New page/slide in the engineering notebook)
Demonstrate what is ‘Done’
  Include a picture of the robot in the current state
  Describe what is done on the robot.
    Include software. Autonomous, driver control
  Describe what you are currently working on
  Describe how your robot performed at the first scrimmage.

## Slide 4: Sprint Retrospective (New page in notebook)
Focusing on how the team worked during the last spring
Answer the following questions in your notebook
  What went well during the sprint
  What did not go well during the sprint
  What improvements will you incorporate during the next sprint

## Slide 5: Design Review/Reevaluation (New slide)
Using what you have learned in the last sprint evaluate you design direction
  What are your priorities?
    Stacks
    Towers
    Autonomous
    …
  What improvements do you want to incorporate into your design?
  What to you want to keep
After the team discussion include your design
  Drawing (Take a picture of hand drawing and include in notebook)
  Description

## Slide 6: Sprint Backlog (10/7 – 11/6)
Build a list of tasks that you commit to completing during the next sprint
Break them down into tasks that can be completed during one class period.
Prioritize the items by their highest Return On Investment (ROI)